# Project Plan v2.0

EduTrack LMS — South African Multi-School Learner Management System

# Learner Management System (LMS)

## Project Plan v2.0 — Maximum Acceleration

### 25 May 2026

Project Owner: Dr. B.A. Tau

Plan Version: 2.0 (Accelerated — 3 Parallel Tracks)

Start Date: 25 May 2026

Pilot Launch Target: 2 August 2026 (10 weeks)

Full Multi-School Launch: October 2026

Curriculum: CAPS (IEB-ready later)

Initial Scope: Grades 4–9

Deployment: Multi-school SaaS — AWS Cape Town (af-south-1)

────────────────────────────────────────────────────────────────────────────────

## 1. The Acceleration Model

Instead of building one module at a time, three development tracks run

simultaneously from Week 1. Each track is handled by a dedicated agent

and produces independently testable output.

TRACK A — BACKEND   : NestJS APIs, Prisma schema, business logic, DB
TRACK B — FRONTEND  : Next.js pages, UI components, forms, dashboards
TRACK C — DEVOPS    : Repo, CI/CD, AWS infrastructure, environments

The only sequential block is the Assessment Engine (Weeks 4–5).

The math behind CAPS SBA calculations must be correct before anything

else can be built on top of it.

────────────────────────────────────────────────────────────────────────────────

## 2. Timeline Overview (10 Weeks to Pilot)

WEEK 1  : Foundation — Schema + Boilerplate + DevOps (all 3 tracks)
WEEK 2  : Core Infrastructure — Auth, Roles, School Onboarding
WEEK 3  : Learner Management — Registration, Student Numbers, Subjects
WEEK 4  : Academic Setup — Timetabling, Attendance (v1)
WEEK 5  : Assessment Engine PART 1 — Architecture + Formative types
WEEK 6  : Assessment Engine PART 2 — SBA engine + Summative + testing
WEEK 7  : Reporting — Report Cards + CAPS Promotion Engine
WEEK 8  : Compliance + Communication — LURITS export + Portals (v1)
WEEK 9  : Finance (v1) + Analytics Dashboard (v1)
WEEK 10 : QA, UAT, Pilot Deployment — 3 schools live

Pilot Launch: Week of 2 August 2026

v2 Feature Enhancements: August–October 2026

Full Multi-School Launch: October 2026

────────────────────────────────────────────────────────────────────────────────

## 3. Guiding Principles

| Principle | In Practice |
| --- | --- |
| CAPS-First | Promotion and SBA calculations hard-coded; no manual config |
| SA-SAMS Compatible | One-click LURITS/EMIS export from Day 1 |
| Load-Shedding Resilient | Offline PWA; IndexedDB; background sync |
| Multi-Tenant from Day One | PostgreSQL RLS; school_id on every table |
| POPI Compliant | Data in af-south-1; audit trails; encryption at rest |
| MVP Discipline | Every module built to v1 (pilot-ready) only; v2 post-pilot |
| Parallel Always | Backend + frontend built simultaneously for every module |

────────────────────────────────────────────────────────────────────────────────

## 4. CAPS Assessment Weightings (Hard-Coded in Engine)

| Phase | Grades | SBA | Final Exam |
| --- | --- | --- | --- |
| Intermediate Phase | 4–6 | 75% | 25% |
| Senior Phase | 7–9 | 60% | 40% |
| FET Phase Gr 10–11 | 10–11 | 40% | 60% |
| FET Phase Gr 12 | 12 | 25% | 75% (NSC) |

These are non-negotiable. No school can override them.

────────────────────────────────────────────────────────────────────────────────

## 5. Tech Stack

| Layer | Technology |
| --- | --- |
| Frontend | Next.js 14 + TypeScript |
| Styling | Tailwind CSS + Shadcn/ui |
| Backend | Node.js + NestJS |
| ORM | Prisma |
| Database | PostgreSQL 16 with Row Level Security |
| Multi-Tenancy | Pool model — shared schema, school_id on all tables |
| Cache / Queues | Redis + BullMQ |
| Auth | NextAuth.js (JWT, tenant-aware, subdomain per school) |
| File Storage | AWS S3 |
| Cloud | AWS af-south-1 (Cape Town — POPI compliant) |
| CI/CD | GitHub Actions |
| Mobile (Phase 2) | React Native + Expo |

────────────────────────────────────────────────────────────────────────────────

## 6. Module Map

### Tier 1 — MVP (Weeks 1–9)

| # | Module | MVP Scope (v1) | Full Scope (v2) |
| --- | --- | --- | --- |
| 1 | School Onboarding & Config | Profile, grades, terms, branding | Multi-branch, fee structures |
| 2 | User Roles & Permissions | 7 roles, RBAC | Custom role builder |
| 3 | Learner Registration | Bio data, guardian, LURITS number | Document uploads, transfers |
| 4 | Student Number Allocation | Auto-generated per school | Custom format config |
| 5 | Subject Choice & Allocation | CAPS catalogue Gr4–9, teacher assign | Gr10–12, IEB catalogue |
| 6 | Timetabling | Manual period grid, basic conflicts | Auto-scheduler, substitutes |
| 7 | Attendance Tracking | Daily register, absence flag | Period-by-period, biometrics |
| 8 | Assessment Engine | All 4 types + CAPS SBA calculator | Rubrics, oral assessments, PAT |
| 9 | Report Cards + Promotion Engine | PDF reports, CAPS promotion logic | Custom templates, digital signatures |
| 10 | SA-SAMS / LURITS Export | Learner + attendance + marks export | Real-time sync |
| 11 | Communication (v1) | Email notifications, absence alerts | SMS, push, two-way chat |
| 12 | Parent + Learner Portal (v1) | Marks, timetable, report cards | Full two-way communication |

### Tier 2 — Growth (Weeks 9–14, post-pilot)

| # | Module |
| --- | --- |
| 13 | Fee & Finance Management |
| 14 | Online Payments (PayFast) |
| 15 | Admissions & Enrolment |
| 16 | Examination Management |
| 17 | Analytics Dashboard |

### Tier 3 — Full Platform (Post-launch)

| # | Module |
| --- | --- |
| 18 | Staff & HR Management |
| 19 | Discipline & Behaviour Tracking |
| 20 | LSEN / Special Needs (IEP/ISSP) |
| 21 | Library Management |
| 22 | Extracurricular Activities |
| 23 | Transport Management |
| 24 | Inventory & Asset Tracking |
| 25 | PAD Platform Integration |

────────────────────────────────────────────────────────────────────────────────

## 7. Phase Detail

────────────────────────────────────────────────────────────────────────────────

### WEEK 1 — Foundation

25 May – 1 June 2026

All three tracks start simultaneously.

#### Track A — Backend

Design complete PostgreSQL schema: all Tier 1 tables

Write Prisma schema file with all models

Define Row Level Security policies for every table

Seed data: CAPS subject catalogue (Gr4–9), SA provinces, districts

Define all API endpoints (OpenAPI spec)

#### Track B — Frontend

Scaffold Next.js 14 project with TypeScript + Tailwind + Shadcn/ui

Set up app router structure: (auth)/, (dashboard)/, (admin)/

Build layout system: sidebar, topbar, breadcrumbs

Build reusable component library: Table, Form, Modal, Badge, Card

Connect to backend API client (axios/fetch wrapper)

#### Track C — DevOps

Create GitHub repository (monorepo: /apps/web, /apps/api, /packages/db)

Set up GitHub Actions: lint → type-check → test → build on every PR

Configure local dev environment: Docker Compose (postgres + redis)

Set up staging environment on AWS (af-south-1)

Configure environment variables management

#### Week 1 Deliverables

[ ] Complete ERD (Entity-Relationship Diagram) for all Tier 1 modules

[ ] Prisma schema file with all models and RLS policies

[ ] GitHub repository live with CI/CD passing

[ ] Next.js app running locally with layout and component library

[ ] Docker Compose environment: postgres + redis + api + web all running

[ ] AWS staging environment provisioned

[ ] OpenAPI specification for all Tier 1 endpoints

────────────────────────────────────────────────────────────────────────────────

### WEEK 2 — Core Infrastructure

2–8 June 2026

#### Track A — Backend

Implement multi-tenant middleware (inject school_id into every request)

Build authentication: login, logout, refresh token, password reset

Build RBAC system: permission guards on all endpoints

Build School Onboarding API (CRUD + validation)

Build User management API (create, assign role, deactivate)

#### Track B — Frontend

Build authentication pages: login, password reset, email verification

Build school onboarding wizard (multi-step form)

Build super-admin dashboard: school list, usage stats

Build user management UI: add/edit/deactivate users, assign roles

Build school settings page: terms, calendar, grade config

#### Week 2 Deliverables

[ ] Login/logout working end-to-end

[ ] JWT with school_id claim; RLS verified (school A cannot see school B data)

[ ] All 7 roles implemented with correct permission matrices

[ ] School onboarding: create school, configure grades and terms

[ ] User management: create teacher, assign to school and role

────────────────────────────────────────────────────────────────────────────────

### WEEK 3 — Learner Management

9–15 June 2026

#### Track A — Backend

Build Learner Registration API (full CRUD, validation, duplicate detection)

Build Guardian management API (create, link to learner, multiple guardians)

Build Student Number allocation engine (auto-generate, duplicate check)

Build CAPS Subject catalogue API (Gr4–9 subjects pre-seeded)

Build Subject allocation API (assign subject to class and teacher)

#### Track B — Frontend

Build learner registration form (all CAPS biographical fields)

Build guardian management UI (add/link/edit guardians)

Build learner profile page (all data in one view, edit inline)

Build learner list page (search, filter by grade/class, bulk actions)

Build CSV import wizard (bulk learner upload with validation preview)

Build subject catalogue and allocation UI

#### Week 3 Deliverables

[ ] Full learner registration end-to-end (register learner, link guardian)

[ ] Student number auto-generated on registration

[ ] Learner search and filter working

[ ] CSV bulk import (test with 200 learners)

[ ] CAPS subjects Gr4–9 allocated to classes and teachers

────────────────────────────────────────────────────────────────────────────────

### WEEK 4 — Academic Setup

16–22 June 2026

#### Track A — Backend

Build Timetable API (period grid, class-subject-teacher-venue links)

Build conflict detection engine (teacher double-booking, venue clashes)

Build Attendance API (daily register capture, absent/present/late)

Build absence flag logic (trigger notification placeholder)

#### Track B — Frontend

Build timetable grid builder (drag-and-drop period assignment)

Build timetable views: per class, per teacher, per venue

Build timetable PDF export

Build attendance capture UI (teacher view: mark register by class)

Build attendance history per learner

Build attendance summary per class and term

#### Week 4 Deliverables

[ ] Timetable builder: periods configured, subjects/teachers assigned

[ ] Basic conflict detection (flags clashes, does not auto-resolve)

[ ] Timetable export to PDF per class and per teacher

[ ] Attendance register: teacher captures daily register in < 2 minutes

[ ] Attendance summary visible on learner profile

────────────────────────────────────────────────────────────────────────────────

### WEEKS 5–6 — Assessment Engine

23 June – 6 July 2026

BOTH TRACKS FOCUSED. THIS IS THE CRITICAL PATH.

No parallelism shortcuts here. Both backend and frontend must be

built, tested, and verified against real CAPS scenarios before

proceeding. One calculation error = wrong report cards.

#### Week 5 — Architecture + Formative Assessment

##### Track A — Backend

Design assessment data model: Task, Mark, MarkBook, ProgrammeOfAssessment

Build assessment task creation API (configurable: type, weight, max mark, term)

Build mark capture API with validation (range checks, missing mark flags)

Build Diagnostic Assessment module (baseline + knowledge gap identification)

Build Learning Profile module (strengths, weaknesses, LSEN flags)

Build Formative Assessment API: Class Test, Assignment, Homework

##### Track B — Frontend

Build Programme of Assessment builder (configure tasks per subject per term)

Build mark capture UI: teacher mark book (grid view, inline editing)

Build diagnostic assessment capture form

Build learning profile record (per learner, editable by teacher)

Build formative assessment UI (create task, capture marks, view results)

#### Week 6 — SBA Engine + Summative + Full Testing

##### Track A — Backend

Build Summative Assessment API (year-end / November exam mark capture)

Build SBA Calculation Engine:

Phase-aware weighting (Gr4-6: 75/25, Gr7-9: 60/40, Gr10-11: 40/60)

Term SBA aggregation per subject per learner

Final mark = weighted(SBA average) + weighted(exam mark)

Build moderation workflow (HOD reviews and approves mark submissions)

Write comprehensive unit tests for ALL calculation scenarios:

All phase combinations (Gr4, Gr5, Gr6, Gr7, Gr8, Gr9)

Edge cases: absent for exam, partial SBA completion, borderline marks

##### Track B — Frontend

Build summative assessment capture UI

Build SBA summary view per learner (term-by-term breakdown)

Build moderation dashboard (HOD view: pending submissions, sign-off)

Build assessment analytics: class average, mark distribution chart

Build mark export (Excel per subject, PDF per learner)

#### Weeks 5–6 Deliverables

[ ] All 4 assessment types capturing marks end-to-end

[ ] SBA calculator verified against manual calculations for all 6 grades

[ ] 100% of unit tests passing for all calculation scenarios

[ ] Moderation workflow: HOD can approve/reject submitted marks

[ ] Mark export working (Excel + PDF)

────────────────────────────────────────────────────────────────────────────────

### WEEK 7 — Report Cards + Promotion Engine

7–13 July 2026

#### Track A — Backend

Build Report Card generation engine (aggregate marks per learner per subject)

Build Promotion Engine with hard-coded CAPS criteria:

Intermediate Phase (Gr4-6): 50% HL, 40% FAL, 40% Maths, 40% NS&T, 40% SS

Senior Phase (Gr7-9): 50% HL, 40% FAL, 40% Maths, 40% in 3 others, 30% rest

FET Phase (Gr10-11): 40% HL, 40% in 2 others, 30% in 3 others

Build progression rules (max 2 years per grade in phase)

Build at-risk learner flagging (mid-term trajectory analysis)

Build override workflow (principal override with audit log)

#### Track B — Frontend

Build report card template (Intermediate Phase layout)

Build report card template (Senior Phase layout)

Build PDF generation (individual and bulk per class/grade)

Build promotion decision view (per class: PROMOTE / REPEAT / PROGRESS)

Build at-risk learner panel (HOD/principal view)

Build override UI (record reason, log to audit trail)

#### Week 7 Deliverables

[ ] Term report cards generated correctly for all Gr4–9 scenarios

[ ] Annual report card with correct final mark (SBA + exam weighted)

[ ] Promotion engine tested against all CAPS scenarios

[ ] Progression rules enforced (cannot flag same grade repeat 3x)

[ ] PDF bulk download: full school report cards in one click

[ ] At-risk flags visible to HOD 4 weeks before term end

────────────────────────────────────────────────────────────────────────────────

### WEEK 8 — Compliance + Communication + Portals

14–20 July 2026

#### Track A — Backend

Build LURITS export: learner biographical data in correct format

Build EMIS export: annual survey data package

Build export validation engine (flag missing required fields)

Build export history and audit log

Build email notification service (SendGrid / AWS SES integration)

Build parent/learner/teacher portal data APIs

(filtered views: marks, timetable, attendance, report cards)

#### Track B — Frontend

Build LURITS export UI (validate → export → download)

Build export history page

Build parent portal: marks, attendance, timetable, report cards

Build learner portal: timetable, assignments, marks

Build teacher portal: mark book, attendance register, class list

Build email notification templates (absence alert, report card ready)

#### Week 8 Deliverables

[ ] LURITS export produces valid output (validated against SA-SAMS spec)

[ ] EMIS export package complete

[ ] Parent portal: parent can log in and see child's full academic record

[ ] Learner portal: learner can view timetable and marks

[ ] Email: absence alert sent automatically when register captured

[ ] Email: report card notification sent on publication

────────────────────────────────────────────────────────────────────────────────

### WEEK 9 — Finance (v1) + Analytics

21–27 July 2026

#### Track A — Backend

Build fee structure API (configure tuition, registration, activity fees)

Build invoice generation engine (per learner, per term)

Build payment recording API (manual payment capture for v1)

Build outstanding debtors query

Build analytics aggregation queries:

Pass rate per grade, per subject, per term

Attendance rate per class and school

At-risk learner count per grade

Subject performance distribution

#### Track B — Frontend

Build fee structure configuration UI

Build invoice list per learner and bulk per grade

Build payment recording UI (record payment, generate receipt)

Build outstanding fees report (sortable, exportable)

Build principal analytics dashboard:

School-wide pass rate card

At-risk learner count

Attendance trend (7-day rolling)

Subject performance table

Build HOD dashboard: subject performance per class

#### Week 9 Deliverables

[ ] Fee invoices generated per learner

[ ] Payment recording and receipt generation

[ ] Outstanding debtors report (export to Excel)

[ ] Principal dashboard: key metrics visible at a glance

[ ] HOD dashboard: subject performance and at-risk count per class

────────────────────────────────────────────────────────────────────────────────

### WEEK 10 — QA, UAT and Pilot Launch

28 July – 3 August 2026

#### Testing Activities

[ ] End-to-end integration tests: full learner journey from registration to report card

[ ] Cross-tenant isolation test: school A cannot access school B data

[ ] Load test: 10 schools, 500 learners each, concurrent mark capture

[ ] LURITS export validation: feed output into SA-SAMS test environment

[ ] PDF generation stress test: 500 report cards simultaneously

[ ] Security audit: POPI compliance check, auth bypass attempts

[ ] Mobile responsiveness check (parent portal on phone)

#### UAT with Pilot Schools

[ ] Run guided UAT with 2–3 school administrators (Hartrog Academy first)

[ ] Run guided UAT with 2–3 teachers (mark capture + report cards)

[ ] Run guided UAT with 2–3 parents (portal access)

[ ] Collect structured feedback, fix critical issues

#### Pilot Deployment

[ ] Deploy to AWS af-south-1 production environment

[ ] Configure custom subdomains (hartrog.lms.co.za etc.)

[ ] Data migration: import existing learner data from pilot schools

[ ] Create admin accounts for school staff

[ ] Conduct 2-hour onboarding session per pilot school

[ ] Open WhatsApp support channel with pilot schools

PILOT LAUNCH TARGET: 2 August 2026

────────────────────────────────────────────────────────────────────────────────

## 8. Post-Pilot Roadmap (August–October 2026)

### August 2026 — v2 Enhancements (based on pilot feedback)

Period-by-period attendance

SMS gateway integration (BulkSMS / Clickatell)

Timetable auto-conflict resolver

Payment gateway (PayFast integration)

Custom report card templates per school

### September 2026 — Tier 2 Modules

Full Admissions & Enrolment module

Examination Management module

Advanced Analytics (year-on-year comparisons)

Grades 10–12 CAPS subject catalogue + combination validator

### October 2026 — Full Multi-School Launch

Self-service school onboarding

Marketing website

Pricing model (per-learner-per-month)

Partner / referral programme

Begin PAD platform integration design

────────────────────────────────────────────────────────────────────────────────

## 9. Risk Register

| # | Risk | Mitigation |
| --- | --- | --- |
| 1 | Assessment calculation error | 100% unit test coverage; manual verification against paper calculations |
| 2 | SA-SAMS export format mismatch | Test export against actual SA-SAMS import in staging before pilot |
| 3 | Load-shedding disrupts pilot | Offline PWA with local storage; built in Week 1 boilerplate |
| 4 | Cross-tenant data leak | PostgreSQL RLS tested end-to-end in Week 2; penetration tested in Week 10 |
| 5 | POPI non-compliance | AWS af-south-1; encryption at rest and in transit; audit logs from Day 1 |
| 6 | Scope creep delays pilot | Strict v1/v2 split; all enhancement requests go to post-pilot backlog |
| 7 | Integration bugs between tracks | Daily sync between backend and frontend agents; shared OpenAPI spec |

────────────────────────────────────────────────────────────────────────────────

## 10. Success Metrics

### By Pilot Launch (2 August 2026)

3 schools onboarded and live

Report cards generated correctly for at least one full term of data

LURITS export accepted by SA-SAMS without errors

Zero cross-tenant data access incidents

### 30 Days Post-Pilot (September 2026)

Net Promoter Score > 40 from school administrators

Teachers capture mark registers in under 3 minutes per class

Report card generation < 30 seconds for 200 learners

At least one school has stopped double-capturing in SA-SAMS

### Full Launch (October 2026)

10+ schools on the platform

Self-service onboarding working (school signs up without manual help)

Platform stable under 50 concurrent schools

────────────────────────────────────────────────────────────────────────────────

## 11. Version History

| Version | Date | Change |
| --- | --- | --- |
| 1.0 | 25 May 2026 | Initial plan — 26 weeks sequential |
| 1.5 | 25 May 2026 | Revised — 14 weeks with some parallelism |
| 2.0 | 25 May 2026 | Maximum acceleration — 10 weeks, 3 parallel tracks |

────────────────────────────────────────────────────────────────────────────────

Document v2.0 | 25 May 2026 | Dr. B.A. Tau / Claude Code

Next action: Begin Phase 0, Week 1 — Full database schema design